# Weekly check-in, Friday 25 September 2026

Prediction market vs rates futures arbitrage. Sean Trew and Nathan Yang, with Richard Howes.

## Where we are

- The method is settled. Both markets are expressed as the probability-weighted expected move in bp at each FOMC meeting, and the signal is the daily gap between the futures-implied move and the Kalshi-implied move over the 60 days before each of the 26 meetings from May 2023 to June 2026.

- The pipeline exists (FRED, Kalshi candlesticks for every outcome, per-month ZQ from TradingView) and works on the May 2023 example. The full 26-meeting run has not completed yet, so we do not have the spread distribution.

- This week we stopped to get organised. We now have a project context document, a definition of done for the current stage, and a written trade and cost memo that answers last week’s question about what the trade is.

## The plan: two stages

Stage 1. Get the Kalshi vs ZQ arb fully working. The idea is simple, so the bar is on execution: reproducible code, cached data, correct formulas, all 26 meetings, convergence and lead/lag tests, written trade rules, fees, net P&L with an out-of-sample split, and a live monitor that runs daily and flags when the rules fire.

Stage 2. Add the reaction function. Feed Kalshi’s CPI and unemployment print markets through a calibrated Taylor rule to get a rule-implied expected move and compare it to both markets. This tells us which market is wrong and why, so the Stage 1 trade has direction and conviction. We will not start it until Stage 1 is signed off.

## Problems found in review this week

- The “>25bp” buckets were valued at 25 or 26bp. They mean at least 50bp, so the Kalshi expected move understates tail outcomes.

- The day-count treated the meeting day as post-decision. The new rate applies from the day after, so the futures-implied move was out by about 3%.

- Kalshi mids from thin books were being read as prices. We are adding a liquidity filter.

- No costs. Kalshi’s taker fee is 7% of P(1−P) per side. On a 50c contract that is 3.5c round trip, about 1.4bp of expected move once the book spread is included. That sets the entry threshold.

## The trade (memo attached)

- A, primary. When the gap is wider than about 3bp on a liquid day, buy the Kalshi bucket that futures say is cheap (or sell the one that is rich). Exit when the gap closes inside 1bp, at the day before the meeting, or on a widening stop. Never hold through the decision.

- B, secondary. Same leg held to settlement, hedged with ZQ (about 2 contracts per 1,000 Kalshi contracts at a mid-month meeting).

- C. The Dutch-book check on the full outcome set.

## Next week

| Ticket | Owner |
| --- | --- |
| Caching for Kalshi, ZQ and FRED pulls | Nathan |
| Formula fixes (threshold buckets, day-count) with unit tests | Nathan |
| Full 26-meeting run to spread_daily.csv | Nathan |
| Liquidity fields and filter | Nathan |
| Spread distribution, convergence and lead/lag analysis | Sean |
| ZQ spot-check against CME settlements | Sean |
| Live monitor spec (daily run, alert rules, log format) | Sean |

## Questions for Richard

- Submission date, and whether the deliverable is the trading system, a strategy paper, or both.

- Does Trade A with a 3bp entry look like a real dislocation in front-end pricing, or is that too tight?

- Should the backtest assume taker fees throughout, or report taker and maker?

- For Stage 2, Fed only, or Fed plus RBA?